## Sept2024
Employee | 2024-09-06 | 2024-09-07 | 2024-09-08 | 2024-09-09 | 2024-09-10 | 2024-09-11 | 2024-09-12 | 2024-09-13 | 2024-09-14 | 2024-09-15 | 2024-09-16 | 2024-09-17 | 2024-09-18 | 2024-09-19 | 2024-09-20 | 2024-09-21 | 2024-09-22 | 2024-09-23 | 2024-09-24 | 2024-09-25 | 2024-09-26 | 2024-09-27 | 2024-09-28 | 2024-09-29 | 2024-09-30
Dwaraknath | 1. Preparation of Sept'24 day wise activity plan. 2. Login, installation and configuartion of NPCI code for development for Sumanth and Vasanth 3. APIs complete endpoint details from NPCI |  |  | 1. NPCI dev status review 2. NPCI functional - transactions wise changes designs 3. Adhoc issues | 1. NPCI dev status review 2. NPCI functional - transactions wise changes designs 3. Meeting with ISO consultant 4. Adhoc issues | 1. NPCI dev status review 2. NPCI functional - transactions wise changes designs 3. Adhoc issues | 1. NPCI dev status review 2. NPCI functional - transactions wise changes designs 3. GAP identification between new fuctional designs with that of already developed 4. Adhoc issues | 1. NPCI dev status review 2. NPCI functional development plan for the month of Sept-24 3. Adhoc issues |  |  | 1. NPCI dev status review f / t 2. NPCI - Axis Bank payment gateway Integration study and development plan. 3. Adhoc issues | 1. NPCI dev status review f / t 2. NPCI - Axis Bank payment gateway Integration study and development plan. 3. Direct - Axis Bank Integration study and development plan. 4. Adhoc issues | 1. NPCI dev status review f / t 2. Direct - Axis Bank Integration study and development plan. 3. Adhoc issues | 1. NPCI dev status review f / t 2. Direct - Axis Bank Integration study and development plan. 3. Adhoc issues | 1. NPCI dev status review f / t 2. Development of Direct - Axis Bank Integration. 3. Adhoc issues |  |  | 1. NPCI dev status review f / t 2. Development of Direct - Axis Bank Integration. 3. Adhoc issues | 1. NPCI dev status review f / t 2. Development of Direct - Axis Bank Integration. 3. Adhoc issues | 1. NPCI dev status review f / t 2. Development of Direct - Axis Bank Integration. 3. Adhoc issues | 1. NPCI dev status review f / t 2. Development of Direct - Axis Bank Integration. 3. Adhoc issues | 1. NPCI dev status review f / t 2. Development of Direct - Axis Bank Integration. 3. Adhoc issues |  |  | 1. NPCI dev status review f / t 2. Development of Direct - Axis Bank Integration. 3. Adhoc issues
Sumanth | Login, installation and configuartion of NPCI code for development |  |  | ReqRegId | ReqMapAIOUtoexistingB2BIDs | ReqActivateEntity ReqEditId | ReqEditInvoice Relay ReqEditInvoice | ReqEditInvoice Relay ReqEditInvoice |  |  | ReqStatusChangeInvoice Relay ReqStatusChangeInvoice | ReqStatusChangeInvoice Relay ReqStatusChangeInvoice | ReqSendCDnote Relay ReqSendCDnote | ReqSendCDnote Relay ReqSendCDnote | ReqConfirmCDnote Relay ReqConfirmCDnote |  |  | ReqConfirmCDnote Relay ReqConfirmCDnote | ReqUpdateCDNoteStatus Relay ReqUpdateCDNoteStatus | ReqUpdateCDNoteStatus Relay ReqUpdateCDNoteStatus | ReqPay Relay ReqPay | ReqPayConfirmation Relay ReqPayConfirmation |  |  | ReqPay Relay ReqPay ------------------------ ReqPayConfirmation Relay ReqPayConfirmation
Vasanth | Login, installation and configuartion of NPCI code for development |  |  | ReqFetchBusinessData | ReqEditBusinessDetails | ReqSendPO Relay ReqSendPO | ReqSendPO Relay ReqSendPO ------------------ ReqConfirmPO Relay ReqConfirmPO | ReqConfirmPO Relay ReqConfirmPO |  |  | ReqEditPO Relay ReqEditPO | ReqEditPO Relay ReqEditPO ---------------- ReqStatusChangePO Replay ReqStatusChangePO | ReqCheckEntityFA Relay ReqCheckEntityFA | ReqCheckEntityFA Relay ReqCheckEntityFA | ReqFARaiseFinancingRequest Relay - ReqFARaiseFinancingRequest |  |  | ReqFARaiseFinancingRequest Relay - ReqFARaiseFinancingRequest | ReqShareFinancingBidswithBusiness Relay - ReqShareFinancingBidswithBusiness | ReqShareFinancingBidswithBusiness Relay - ReqShareFinancingBidswithBusiness | ReqFAResponsetoBidAPI Relay - ReqFAResponsetoBidAPI | ReqFAResponsetoBidAPI Relay - ReqFAResponsetoBidAPI |  |  | Buffer
Ravi
Rajaiah